Spring 2023 Research Project Outline

Mentor Name(s): Liam Dubay

Mentee Name(s):

Project Title: Chemical Cartography of the Milky Way

In a short paragraph, explain the project and its learning objectives:

The elemental abundances we observe in stars are the products of multiple different nucleosynthetic yields, in particular Type Ia and Type II supernovae. The distribution of stellar abundances across the Galactic disk can tell us a lot about the formation history of the Milky Way galaxy. In the course of this project, my mentee will learn about the APOGEE survey and how to handle and plot large astronomical datasets. They will also learn the basics of stellar life cycles and how supernovae affect the chemical abundances of stars.

What are the deliverables? (i.e. plot/figure/image/equation mentee will reach)

A plot of the bimodal distribution of stellar abundances from APOGEE in [Mg/Fe] vs [Fe/H] space, showing how it changes in different regions in the galactic disk. If time, possibly a plot of a simple chemical evolution model run in VICE.

Project Calendar: Indicate what the mentee will be expected to do each week. Work days are indicated in the left column. Include estimated time, resources, in/out of class work, and whether it is completed on their own or with you. The project should take 8-10 hours in total.

| Dates: | Tasks: |
| --- | --- |
| Week 1 (2/13-2/19) Intro to Project & Work Day | In class: set up data access via SciServer and use Star in a Box to learn about stellar life cycles (1 hour w/ mentor) Out of class: explore the SDSS website and write a 1-para summary of the APOGEE survey (30 mins w/o mentor) |
| Week 2 (2/20-2/26) Lecture Day Outside of Class Work | Out of class: read Wikipedia pages on Type Ia & Type II supernovae, write a 1-paragraph summary of each, and find an image of a Type Ia and Type II remnant (1 hour w/o mentor) |
| Week 3 (2/27-3/5) In Class Work Day | In class: introduction to handling large datasets in Python with pandas (1 hour w/ mentor) Out of class: read Hayden et al. (2015) abstract and sections 1, 3.1, and 5, and make a note of any questions that come up (3.5 pages and 2 plots; 1 hour w/o mentor) |
| Week 4 (3/6-3/11) Careers In STEM Outside of Class Work | Out of class: go through pre-prepared notebook showing how to load APOGEE data and exploring the dataset (1 hour w/o mentor) |
| Week 5 (3/20-3/26) In Class Work Day | In class: plot [Mg/Fe] vs [Fe/H] and discuss what we can learn from it. If time, learn how to make subplots in different galactic regions (1 hour w/ mentor) Out of class: write a summary of the plot (30 mins w/o mentor) |
| Week 6 (3/27-4/2) How to Make a Poster Lecture Outside of Class Work | Out of class: write a summary of last week’s plot plus a summary of what you learned during this project (1 hour w/o mentor) |
| Week 7 (4/3-4/9) Lecture Day Outside of Class Work | Out of class: extra time if schedule slips, or go through notebook demonstrating simple models of chemical evolution (1 hour w/o mentor) |
| Week 8 (4/10-4/16) LAST Work Day Presentations (4/17) | In class: go over poster with mentor (1 hour w/mentor) Out of class: finish poster (1 hour w/o mentor) |

Reading List: (Make sure material is level appropriate.)

- Star in a Box

- Type Ia supernovae (Wikipedia)

- Type II supernovae (Wikipedia)

- Overview of APOGEE from the SDSS-IV website

- Selections from Hayden et al. (2015)

- Using APOGEE Stellar Abundances (technical resource for reference)

Resource List:  (This should include lab space, instruments, and software. Note that mentees are not allowed to complete research projects that require safety training operation of lab equipment. If you feel this is detrimental to your project, please petition Polaris leadership.)

Jupyter notebooks hosted on SciServer and accessed from a laptop or tablet.

Other Notes:

There are a lot of nuances when it comes to working with the APOGEE dataset, like dealing with FITS files and quality cuts, that I will handle behind the scenes because they would take too much time. The goal is for my mentee to practice handling large scientific data sets, not worry about FITS files and bitmask flags.